## Project Overview
InvestorConnect - 2 Month Development Plan
Project Name: | InvestorConnect (InfiniteTechAI Platform)
Duration: | 60 Days (2 Months)
Team Size: | 4 Members
Start Date: | 2026-01-20
End Date: | 2026-03-21
Team Structure:
Member 1: | Startup Portal Lead (Full Stack)
Member 2: | Investor Portal Frontend Lead
Member 3: | Investor Portal Backend Lead
Member 4: | Admin & Shared Services (Auth, DevOps, QA)
Timeline Phases
Month 1: Weeks 1-2 | Foundations & Core Auth | Environment, DB, Auth System, Basic UI Layouts
Month 1: Weeks 3-4 | Core Profiles & Pitches | Startup/Investor Profiles, Pitch Feed, Basic Flow
Month 2: Weeks 5-6 | Connectivity & Messaging | Real-time Chat, Connections, Notifications, Watchlist
Month 2: Weeks 7-8 | Advanced Features & Launch | Admin Dashboard, Analytics, Security Audit, Deployment

## Daily Tasks (60 Days)
Day | Date | Member 1 (Startup) | Member 2 (Investor FE) | Member 3 (Investor BE) | Member 4 (Admin/Infra) | Milestone
Day 1 | 2026-01-20 | Frontend Repo Init, React+Vite Setup | Investor Repo Init, UI Lib Installation | Backend Repo Init, FastAPI Setup | Docker Compose Setup, DB Config | Project Kickoff 🚀
Day 2 | 2026-01-21 | Landing Page Initial Layout | Investor Auth Pages (Login/Register) | User Models & Database Schema | Auth Service (JWT, OAuth base)
Day 3 | 2026-01-22 | Startup Auth Pages (Login/Register) | Setup Tailwind & Design System | Auth API Endpoints (Login/Reg) | Email Service Integration (SendGrid/SMTP)
Day 4 | 2026-01-23 | Connect Auth to Backend | Connect Auth to Backend | Middleware & Error Handling | CI/CD Pipeline Basic Setup
Day 5 | 2026-01-24 | Onboarding Wizard Flow (UI) | Onboarding Wizard Flow (UI) | Profile Creation API | S3/Storage Setup for Files | Auth System Ready
Day 6 | 2026-01-25 | Code Review & Refactor | Code Review & Refactor | Code Review & DB Optimization | Infrastructure Monitoring Setup | Weekend Catchup
Day 7 | 2026-01-26 | Rest/Planning | Rest/Planning | Rest/Planning | Rest/Planning | Sunday
Day 8 | 2026-01-27 | Startup Profile Page UI | Investor Profile Page UI | Profile CRUD Endpoints | Admin User Management Dashboard
Day 9 | 2026-01-28 | Edit Profile Functionality | Edit Profile Functionality | File Upload API (Logos/Avatars) | Image Optimization Service
Day 10 | 2026-01-29 | Startup Dashboard Shell | Investor Dashboard Shell | Dashboard Stats API (Mock Data) | Logging & Auditing System
Day 11 | 2026-01-30 | Integration of Profile API | Integration of Profile API | Dashboard Logic Implementation | Verification Flow (Email/Phone)
Day 12 | 2026-01-31 | Pitch Creation Form UI (Step 1-2) | Browse Startups Grid UI | Pitch Models & Creation API | Admin Approval Workflow Backend | Profiles Complete
Day 13 | 2026-02-01 | Testing Profile Flows | Testing Profile Flows | Unit Tests for Profiles | Security Headers & CORS Config
Day 14 | 2026-02-02 | Rest | Rest | Rest | Rest
Day 15 | 2026-02-03 | Pitch Form (Financials/Docs) | Advanced Filters (Industry/Stage) | Pitch Upload & Document API | Document Security & Encryption
Day 16 | 2026-02-04 | Pitch Preview & Submit | Detailed Startup View Modal | Pitch Query/Filter API | Admin Pitch Review Interface
Day 17 | 2026-02-05 | My Pitches Management UI | Investment Logging Form UI | Investment Tracking API | Data Analytics Base Setup
Day 18 | 2026-02-06 | Pitch Analytics View | Portfolio Dashboard UI | Portfolio Logic & Calculations | Report Generation Service (PDF)
Day 19 | 2026-02-07 | Integration of Pitch API | Integration of Feed API | Feed Algorithm (Basic) | Matching Algorithm (Basic) | Pitch Flow Ready
Day 20 | 2026-02-08 | Fix UI Bugs (Forms) | Fix UI Bugs (Grids) | Optimize Feed Query | Load Testing Feed
Day 21 | 2026-02-09 | Rest | Rest | Rest | Rest
Day 22 | 2026-02-10 | Chat List UI | Chat List UI | Message Models & Basic API | WebSocket Server Setup
Day 23 | 2026-02-11 | Chat Room/Conversation UI | Chat Room/Conversation UI | Send/Receive API Endpoints | Real-time Event Broadcasting
Day 24 | 2026-02-12 | Connect WS to Frontend | Connect WS to Frontend | WS Authentication Handler | Redis for Pub/Sub (Scalability)
Day 25 | 2026-02-13 | Message States (IsTyping/Read) | Message States (IsTyping/Read) | Read Receipts Backend | Message Persistence & History
Day 26 | 2026-02-14 | File Sharing in Chat UI | File Sharing in Chat UI | Chat File Sharing API | Malware Scanning Service | Messaging MVP
Day 27 | 2026-02-15 | Integration Testing Chat | Integration Testing Chat | WS Stress Testing | Server Scaling Config | Month 1 Review
Day 28 | 2026-02-16 | Rest | Rest | Rest | Rest
Day 29 | 2026-02-17 | Connection Request UI | Find Investors Page | Connections API & Network Graph | Notification Service (Brain)
Day 30 | 2026-02-18 | Network Management Page | Connection Request Handling | Connection Logic & Constraints | Push Notification Integration
Day 31 | 2026-02-19 | Notifications Dropdown UI | Notifications Dropdown UI | Notification Trigger System | Email Digests System
Day 32 | 2026-02-20 | In-App Notification Stream | In-App Notification Stream | Real-time Notification WS | Activity Logs System
Day 33 | 2026-02-21 | Settings: Notifications | Settings: Notifications | Preferences API | GDPR/Compliance Tools | Social Features Done
Day 34 | 2026-02-22 | Catchup / Polish | Catchup / Polish | Catchup / DB Migrations | Backup System Test
Day 35 | 2026-02-23 | Rest | Rest | Rest | Rest
Day 36 | 2026-02-24 | Data Room Manager UI | Data Room Viewer UI | Data Room Permissions API | Access Logs & Audit Trails
Day 37 | 2026-02-25 | Upload Financials Logic | Download Tracking Logic | Secure File Delivery API | Watermarking Service
Day 38 | 2026-02-26 | Meeting Scheduler Integration | Calendar View Integration | Meeting API & Calendar Sync | Google/Outlook Calendar Integration
Day 39 | 2026-02-27 | Task/To-Do List Widget | Watchlist & Notes Widget | Tasks & Notes API | Search Engine (Elastic/PGSearch)
Day 40 | 2026-02-28 | Global Search Bar UI | Global Search Bar UI | Global Search API | Search Indexing Service | Tools Complete
Day 41 | 2026-03-01 | Review Tools UX | Review Tools UX | API Performance Tuning | DB Index optimization
Day 42 | 2026-03-02 | Rest | Rest | Rest | Rest
Day 43 | 2026-03-03 | Startup Analytics Dashboard | Investor AI Recommendations | Analytics Aggregation API | Super Admin Dashboard Setup
Day 44 | 2026-03-04 | Export Reports Function | Export Reports Function | Detailed Report Generation API | Admin User Moderation Tools
Day 45 | 2026-03-05 | Feedback/Support Form | Feedback/Support Form | Support Ticket API | Admin Support Queue
Day 46 | 2026-03-06 | Polish: Loading States | Polish: Empty States | Backend Caching Layer | System Health Dashboard
Day 47 | 2026-03-07 | Polish: Error Boundaries | Polish: Animations | API Rate Limiting Finals | Security Pen-Testing (Self) | Feature Freeze
Day 48 | 2026-03-08 | Bug Fixing | Bug Fixing | Bug Fixing | Bug Fixing
Day 49 | 2026-03-09 | Rest | Rest | Rest | Rest
Day 50 | 2026-03-10 | End-to-End Testing (User Flow) | End-to-End Testing (User Flow) | Final API Tests | Production Environment Setup | Start QA
Day 51 | 2026-03-11 | Fix Critical Bugs | Fix Critical Bugs | Fix Critical Bugs | SSL & Domain Config
Day 52 | 2026-03-12 | Final UI Polish | Final UI Polish | Database Final Migration | CDN & Asset Optimization
Day 53 | 2026-03-13 | Documentation (User Manual) | Documentation (Videos) | API Docs Finalizing | Deployment Runbook
Day 54 | 2026-03-14 | Pre-Launch Check | Pre-Launch Check | Pre-Launch Check | Go-Live execution | GO LIVE 🚀
Day 55 | 2026-03-15 | Post-Launch Monitoring | Post-Launch Monitoring | Live Log Monitoring | Incident Response Watch
Day 56 | 2026-03-16 | Victory Lap | Victory Lap | Victory Lap | Victory Lap | PROJECT COMPLETE

## Member 1 - Startup Lead
Member 1: Startup Portal Lead (Full Stack)
Component | Detailed Tasks | Priority | Est. Hours | Status
Auth & Onboarding | Signup, Login, Wizard Flow, Email Verification | High | 8 | Pending
Startup Profile | Profile Form, Team Members, Logo Upload, Social Links | High | 8 | Pending
Pitch Management | Create Pitch Flow, Edit Pitch, Document Uploads | High | 8 | Pending
Dashboard | Analytics Widgets, Recent Visitors, Notifications Feed | High | 8 | Pending
Investor Search | Search Interface, Filters, Investor Profiles View | Medium | 8 | Pending
Messaging UI | Chat Interface, File Sharing, Contacts List | High | 8 | Pending
Settings | Account Settings, Privacy, Notifications Preferences | Low | 8 | Pending

## Member 2 - Investor FE
Member 2: Investor Portal Frontend Lead
Component | Detailed Tasks | Priority | Est. Hours | Status
Auth & Onboarding | Investor Signup, KYC Flow, Thesis Definition | High | 8 | Pending
Discovery | Startup Feed, Specialized Filters, Search, Recommendation Cards | High | 8 | Pending
Due Diligence | Startup Details Modal, Data Room Viewer, Q&A Section | High | 8 | Pending
Portfolio | My Investments, Performance Charts, Add Investment Flow | High | 8 | Pending
Pipeline | Kanban Board for Deal Flow, Notes, Status Updates | Medium | 8 | Pending
Social | Networking Interface, Messaging, Calendar/Meetings | Medium | 8 | Pending
Reporting | Export to PDF/Excel, Portfolio Summary | Low | 8 | Pending

## Member 3 - Investor BE
Member 3: Investor Portal Backend Lead
Component | Detailed Tasks | Priority | Est. Hours | Status
Core API | User CRUD, Authentication, Profile Management | High | 8 | Pending
Pitch Engine | Pitch CRUD, Feed Algorithm, Search Optimization | High | 8 | Pending
Matching Logic | Score Calculation, Recommendation Engine | High | 8 | Pending
Investment API | Portfolio Tracking, Transaction Records, Analytics | High | 8 | Pending
Communication | Messaging Endpoints, Notification Triggers | High | 8 | Pending
Data Room | Secure File Upload/Download, Access Control Lists | Medium | 8 | Pending
Integrations | Calendar Sync, External Data Sources | Low | 8 | Pending

## Member 4 - Admin & Infra
Member 4: Admin & Shared Services Lead
Component | Detailed Tasks | Priority | Est. Hours | Status
Infrastructure | Docker Setup, CI/CD, Database Management, Backups | High | 8 | Pending
Security | Auth Service (OAuth), Rate Limiting, CORS, Encryption | High | 8 | Pending
Admin Dashboard | User Management, Content Moderation, Analytics | High | 8 | Pending
Notification Svc | Push/Email Service, Template Management, Queues | Medium | 8 | Pending
Real-time Svc | WebSocket Server, Redis Integration, Event Bus | High | 8 | Pending
DevOps | Monitoring (Prometheus/Grafana), Logging (ELK) | Medium | 8 | Pending
Compliance | GDPR Tools, Data Export, Audit Logging | Low | 8 | Pending

## Progress Tracker
Weekly Progress Tracker
Week | Planned Tasks | Completed Tasks | Completion % | Notes
Week 1 | 28 | 0
Week 2 | 28 | 0
Week 3 | 28 | 0
Week 4 | 28 | 0
Week 5 | 28 | 0
Week 6 | 28 | 0
Week 7 | 28 | 0
Week 8 | 28 | 0