## Project Overview
InvestorConnect - 1 Month Development Plan
Project Name: | InvestorConnect (InfiniteTechAI Platform)
Duration: | 30 Days
Team Size: | 3 Members
Start Date: | 2026-01-20
End Date: | 2026-02-19
Team Structure:
Member 1: | Startup Portal (Frontend + Backend)
Member 2: | Investor Portal (Frontend)
Member 3: | Investor Portal (Backend + Infrastructure)
Weekly Breakdown
Week 1 (Days 1-7) | Foundation & Core Features | Setup, Auth, Basic UI
Week 2 (Days 8-14) | Advanced Features | Messaging, Portfolio, Data Rooms
Week 3 (Days 15-21) | Integration & Testing | API Integration, Bug Fixes, Testing
Week 4 (Days 22-30) | Deployment & Polish | Production Deploy, Documentation, Final QA

## Daily Tasks
Day | Date | Member 1 (Startup) | Member 2 (Investor FE) | Member 3 (Investor BE) | Milestone
Day 1 | 2026-01-20 | Setup Startup Portal repo, Docker config, Basic routing | Setup Investor Portal repo, Install dependencies, Create layout | Database schema design, Setup PostgreSQL, Create base models | Environment Setup
Day 2 | 2026-01-21 | Create Signup page UI, Form validation, Error handling | Create Login page UI, Design system setup, Color palette | Auth endpoints (register, login), JWT implementation, Password hashing
Day 3 | 2026-01-22 | Create Login page, Integrate auth API, Token storage | Dashboard layout, Sidebar navigation, Header component | User profile endpoints, Role-based access control, Session management | Auth Complete
Day 4 | 2026-01-23 | Dashboard UI, Stats cards, Recent activity feed | Browse Pitches page layout, Filter UI, Search bar | Pitch feed API, Filtering logic, Search implementation
Day 5 | 2026-01-24 | Company Profile page, Edit mode, Form handling | Pitch detail modal, Comments section UI, Rating stars | Startup profile CRUD, Pitch CRUD endpoints, File upload setup | Core Pages Done
Day 6 | 2026-01-25 | Pitch creation form, File upload UI, Preview mode | Portfolio page layout, Investment cards, Stats dashboard | Investment tracking API, Portfolio analytics, Data aggregation
Day 7 | 2026-01-26 | Review & fix Week 1 bugs, Code cleanup, Documentation | Review & polish UI, Responsive fixes, Accessibility | Database optimization, API performance tuning, Error handling | Week 1 Review
Day 8 | 2026-01-27 | Messages page UI, Conversation list, Chat interface | Messages page UI (investor side), User search, Chat UI | Messaging API, WebSocket setup, Real-time notifications | Messaging Start
Day 9 | 2026-01-28 | File sharing in messages, Image preview, PDF support | Watchlist page, Add/remove functionality, Watchlist cards | Watchlist API, Connection requests API, Status management
Day 10 | 2026-01-29 | Notifications UI, Notification bell, Mark as read | In Review page, Pipeline view, Drag-drop (optional) | Notifications backend, Push notifications, Email triggers | Notifications Done
Day 11 | 2026-01-30 | Investor discovery page, Filter by criteria, Connect button | Data Room component, Document viewer, Download tracking | Data room API, Document storage, Access control
Day 12 | 2026-01-31 | Settings page, Profile photo upload, Password change | Meeting scheduler UI, Calendar integration, Time slots | Meeting API, Google Calendar integration, Email reminders | Settings Complete
Day 13 | 2026-02-01 | Analytics dashboard, Charts, Export functionality | Log Investment page, Form validation, Document upload | Investment logging API, Portfolio stats, Growth tracking
Day 14 | 2026-02-02 | Review & fix Week 2 bugs, Integration testing, Polish | Review & UI refinement, Cross-browser testing, Mobile fixes | API testing, Load testing, Security audit | Week 2 Review
Day 15 | 2026-02-03 | End-to-end testing (Signup → Pitch creation) | End-to-end testing (Browse → Investment logging) | Integration testing, API documentation, Postman collection | Testing Phase
Day 16 | 2026-02-04 | Fix critical bugs, Edge case handling, Error messages | Fix UI bugs, Loading states, Empty states | Fix backend bugs, Database migrations, Data validation
Day 17 | 2026-02-05 | Performance optimization, Code splitting, Lazy loading | Performance optimization, Image optimization, Caching | Database indexing, Query optimization, Caching layer | Performance Tuning
Day 18 | 2026-02-06 | Security review, XSS prevention, CSRF tokens | Security review, Input sanitization, Auth checks | Security hardening, SQL injection prevention, Rate limiting
Day 19 | 2026-02-07 | User acceptance testing, Feedback collection, Bug fixes | User acceptance testing, UI/UX improvements, Polish | Monitoring setup, Logging, Error tracking (Sentry) | UAT Complete
Day 20 | 2026-02-08 | Documentation, User guide, Feature walkthrough | Documentation, Component library, Style guide | API documentation, Deployment guide, Architecture docs
Day 21 | 2026-02-09 | Review & final polish, Regression testing, Sign-off | Review & final polish, Accessibility audit, Final QA | Review & final checks, Backup strategy, Rollback plan | Week 3 Review
Day 22 | 2026-02-10 | Production build, Environment variables, Config | Production build, Asset optimization, CDN setup | Production database setup, Migrations, Seed data | Deployment Prep
Day 23 | 2026-02-11 | Deploy to staging, Smoke testing, Bug fixes | Deploy to staging, Cross-browser testing, Mobile testing | Deploy backend to staging, Health checks, Monitoring
Day 24 | 2026-02-12 | Production deployment, DNS setup, SSL certificates | Production deployment, CDN configuration, Analytics | Production deployment, Database backups, Scaling config | Production Live
Day 25 | 2026-02-13 | Post-deployment monitoring, Bug fixes, Hot fixes | Post-deployment monitoring, User feedback, Quick fixes | Post-deployment monitoring, Performance monitoring, Alerts
Day 26 | 2026-02-14 | Feature enhancements, User feedback implementation | UI polish, Animation improvements, Micro-interactions | Performance improvements, Database tuning, Caching
Day 27 | 2026-02-15 | Final documentation, Video tutorials, User onboarding | Final documentation, Design system docs, Component docs | Final documentation, API changelog, Runbook | Documentation Complete
Day 28 | 2026-02-16 | Handover preparation, Knowledge transfer, Training | Handover preparation, Design handoff, Asset delivery | Handover preparation, Infrastructure docs, Access setup
Day 29 | 2026-02-17 | Final review, Retrospective, Lessons learned | Final review, Retrospective, UI/UX insights | Final review, Retrospective, Technical debt log
Day 30 | 2026-02-18 | Project closure, Archive, Celebration! 🎉 | Project closure, Portfolio update, Celebration! 🎉 | Project closure, Monitoring handoff, Celebration! 🎉 | Project Complete! 🚀

## Member 1 - Startup
Member 1: Startup Portal Developer
Feature | Tasks | Priority | Status
Authentication | Signup page, Login page, Password reset, Email verification | High | Pending
Dashboard | Stats overview, Recent activity, Quick actions, Notifications | High | Pending
Company Profile | Profile form, Edit mode, Logo upload, Social links | High | Pending
Pitch Creation | Multi-step form, File upload, Preview, Draft saving | High | Pending
Investor Discovery | Browse investors, Filter by criteria, Connection requests | Medium | Pending
Messaging | Chat interface, File sharing, Conversation list, Notifications | High | Pending
Analytics | Pitch views, Investor interest, Engagement metrics | Medium | Pending
Settings | Profile settings, Password change, Notifications preferences | Low | Pending

## Member 2 - Investor FE
Member 2: Investor Portal Frontend
Feature | Tasks | Priority | Status
Dashboard | Portfolio stats, Recent pitches, Activity feed, Quick filters | High | Pending
Browse Pitches | Grid/List view, Filters, Search, Sort options, Pitch cards | High | Pending
Pitch Details | Modal view, Comments, Ratings, Data room access, Actions | High | Pending
Portfolio | Investment list, Stats cards, Growth charts, Export | High | Pending
Watchlist | Saved pitches, Add/remove, Notes, Reminders | Medium | Pending
In Review | Pipeline view, Status updates, Notes, Decision tracking | Medium | Pending
Messages | Chat UI, User search, File preview, Notifications | High | Pending
Meetings | Calendar view, Schedule meeting, Time slots, Reminders | Low | Pending
Reports | Export reports, PDF generation, Charts, Custom filters | Low | Pending

## Member 3 - Investor BE
Member 3: Investor Portal Backend
Feature | Tasks | Priority | Status
Authentication API | Register, Login, JWT, Password reset, Email service | High | Pending
User Management | Profile CRUD, Role management, Permissions | High | Pending
Pitch API | CRUD operations, Feed endpoint, Search, Filters, Sorting | High | Pending
Investment API | Log investment, Portfolio stats, Analytics, Export | High | Pending
Messaging API | Send/receive messages, File upload, WebSocket, Notifications | High | Pending
Data Room | Document upload, Access control, Download tracking | Medium | Pending
Connections | Request/accept/reject, Status management, Notifications | Medium | Pending
Notifications | Create notifications, Mark read, Push notifications | Medium | Pending
Infrastructure | Docker setup, Database migrations, Monitoring, Backups | High | Pending
Security | Rate limiting, Input validation, SQL injection prevention | High | Pending

## Progress Tracker
Weekly Progress Tracker
Week | Planned Tasks | Completed Tasks | Completion % | Notes
Week 1 | 21 | 0 |  | Foundation & Core Features
Week 2 | 21 | 0 |  | Advanced Features
Week 3 | 21 | 0 |  | Integration & Testing
Week 4 | 27 | 0 |  | Deployment & Polish